## Introduction
Root Causes | Definition
Vendor Bug | Netwoven or Ascentiant coding or incomplete testing resulted in function or interface not working.
Sutter RDD Bug | RDD Development coding or incomplete testing resulted in function or interface not working.
Data Reality Check | Production data revealed surprises, creating a different user experience than anticipated.
Missed Requirement | Product did not include requirement that was in documented scope and requirements documentation.
Missed Specification | Product functional specification does not align with need of customer and/or documented requirement.
Missed Analysis | Product does not function as defined by requirement.
Infrastructure | Data movement between source and component, transition of dashboard and other related ability not working as planned, designed or required.
New Requirement/Spec | Customer has identified a new requirement and/or specification.
Categories | Definition
Defects | Product feature, function does not work as designed per requirements.
Enhancements | Product feature does not exist in current scope and customer would like change and/or add this to product.
Integration | This includes all interfaces, API and data sourcing activities. If issues arise in these areas "Integration" is to be used.
Workflow | Product dashboard and User interaction must flow per a defined workflow/process. If system or workflow are not aligned, use this category.

## MS-Share Defects
Defects - Function | Defects - Visual | Enhancements | Spec Mismatch | Integration | Workflow | Category | Sutter Status | Last Updated by, when: | Jackie Liu tested bug fixes 10/19-10/20. | [7 empty] | Root cause List |  | Patient Concerns | Defect Type List
27 | 26 | 4 | 11 | 0 | 0 | Total | 68 | [7 empty] | Defect / Enhancement Summary |  | Vendor Bug |  | Graph / DMTs | Defect - Visual
3 | 0 | 1 | 4 | 0 | 0 | Resolved | 8 |  |  |  |  | Designated Status |  | (Not started = under review) | Resolved Status: |  | Sutter RDD Bug |  | Graph / Other Meds | Defect - Function
18 | 6 | 1 | 2 | 0 | 0 | In Progress | 27 |  |  |  |  | Resolved: Fixed/Validated | In Progress | Not Started | Developer: Resolved means it's FIXED. Indicate Release and Date in column L. If not validated by Sutter, reverts to "In Progress" |  | Data Reality Check |  | Graph / Vit D | Spec Mismatch
4 | 2 | 0 | 2 | 0 | 0 | Under Review | 8 |  |  |  |  | Code 3 | Code 2 | Code 1 | Sutter Tech Team: Once fixed by developer, Resolved means it has been VALIDATED in the designated test environment |  | Missed Requirement |  | Graph / EDSS | Enhancement
[11 empty] | Developer Inputs |  |  |  |  | Missed Specification |  | Graph / Labs
Date Reported | Date Closed *by Sutter* | Type | Reported By | Priority | Assigned To | Reference # | Component | Issue | Requirement Reference (if application, refer to what requirement is this aligned to) | Sutter "Reviewed" Release (NCD=Netwoven Code Drop; ACD=Ascentiant Code Drop, RCD=RDD Code Drop) | DEVELOPER "Fix" Release, Date | DEVELOPER Designated Status | SUTTER Designated Status | Root Cause | Comments and Sutter Remedy Description as needed (Place most recent comments at botton, with date) | Missed Analysis |  | Graph / 25' Walk
2017-09-12 |  | Spec Mismatch | Anish | High | Netwoven | D00001 | CDS | When is checkbox state in CDS section saved? A CDS checkbox can be changed in a number of ways (a selection can be made in the left panel or demographics bar, or a CDS checkbox can be manually checked/unchecked). Do we want to save the state every time a checkbox is toggled, or based on some other event? |  | NCD.1 |  | 2 | 3 | Data Reality Check | JS - screen shots, more details, etc. 10/12 ML: Sushant is identifeid as Netwoven owner and NW status is in progress but no indication of how it will be resolved. Viraj/Sushant, please communicate with Anish to review optimal solution. 10/17 - complete per Anish. Resolution: A CDS checkbox can be changed in a number of ways (a selection can be made in the left panel or demographics bar, or a CDS checkbox can be manually checked/unchecked). Do we want to save the state every time a checkbox is toggled, or based on some other event? Every time a checkbox is toggled we need to call the PUT API. | New Requirement/Spec |  | Graph / Relapses
2017-09-12 |  | Spec Mismatch | Anish | High | Netwoven | D00002 | CDS | How is CDS state determined in conflicting situations? Suppose the application is loaded without any state for the current CSN. On application load, the DMT checkbox is checked in the left panel, causing the DMT checkbox to be checked in CDS. Next, assume the clinician unchecks DMT in CDS and that state is saved in the back end. When the application is loaded again, the CDS panel is loaded with DMT unchecked, but then the left panel with load with DMT checked, which in turn will cause CDS panel to check the DMT checkbox. So it will appear that the saved state of DMT did not load correctly. |  | NCD.1 | NCD 3, 10/11/17 | 3 | 3 | Missed Specification | 10/12 ML: Sushant identifed as Netwoven owner. He says: The data related to Neuro coming from Server....Will update later. Viraj/Sushant, clarify the "resolved" action and communicate w/ Anish for his review/approval. 10/17: Per Anish, this is resolved. Here’s what we decided: We need to load the saved state of the checkboxes whenever the application is re-loaded for a given CSN …EXCEPT for the three default checked elements on the MS Related panel – DMT, EDSS and Labs – the corresponding checkboxes on the CDS panel should always be checked when the application is re-loaded regardless of what their saved state was | Infrastructure |  | Graph / Symptoms
2017-09-12 |  | Spec Mismatch | Anish | High | Frank | D00003 | Other | Where are the error messages shown to the user in the application? |  | NCD.1 |  | 1 | 3 | Missed Specification | 10/13 ML: Ask Frank to review (and validate w/ HCS if needed) where error messages *should* be displayed as a standard practice, and share that spec w/ Netwoven. Indicate the desired spec here. 10/17: Per Anish, this is resolved. In general for all components we want to show the error message where the data is supposed to appear (rather than a pop-up). |  |  | Graph / Imaging
2017-09-12 |  | Spec Mismatch | Anish | High | Anish | D00004 | Graph / DMTs | In certain cases, the medStart date is missing for a certain medication. In these cases, how is the starting date of the bar graph for that medication decided? Should we assume that the start date is the Order Date of the medication. |  | NCD.1 | NCD 3, 10/11/17 | 3 | 3 | Data Reality Check | JS - No start date is available in EPIC. Will need to determine a approach. ML 10/12: NW (Anupam is defect owner) says: Yes, as per current implementation, in certain cases the medStart date is missing for a certain medication, then YES the start date is the Order Date of the medication. ML 10/13: Ask Anish/Frank to validate this approach (using order date if start date is missing) with Eileen. Indicate the desired spec here. 10/17: Per Anish, this is resolved. For all meds, use the order start date for the bar graph. Don’t look at the med start date at all even if the value if present in the API response. However, for DMTs, in data layer 2, the provider can enter a patient reported start date – mm/yyyy. If this has been saved then use that for the DMT bar graph instead of the order date. |  |  | CDS
2017-09-26 |  | Spec Mismatch | Anish | High | Anish | D00005 | Graph / EDSS | DSS Core update implementation. Requirement vs. deliverable not aligned. The issue with the spec was that it was asking to display an "Update" button on both in the first popup (that shows the editable text box for the score) AND the second popup (that shows the scorecard of descriptions for each score). Clicking two updates would be confusing to the user. Anish Arora [11:57 AM] ok ..so for EDSS spec, I don't think for updating the score you need ot launch the pop-up where they select the score. That is just a strightforward entry. The score selection box only pops up when the doctor is "adding" a new score using the + button. Viraj Bais [12:10 PM] The way we were interpreting the spec (Page 16, first table cell, 2nd bullet from the bottom) that for updates, the score selection popup needs to be launched with the "Add" button changed to an "Update" button. [12:10] If the encounter is NOT closed, then you can click the datapoint and this will then bring up the form and the button would say “Update” (instead of “Add”). There will always be only one record per provider entered EDSS score. There is need to maintain history tracking. [12:11] This text was in the context of the scorecard. Anish Arora [12:18 PM] The "datapoint" in the above sentence means the point on the graph (the symbol). The form means the pop-up when you click on the symbol. Anish Arora [12:19 PM] so over here the doctor can change 3.5 to whatever value they want (say 4) and then click the "Update" button. [12:20] I don't believe the spec said to show the big score selection pop-ups here |  | NCD.1 |  | 1 | 2 | Vendor Bug | 9/28 JS - Conversation between Anish and Viraj regarding interpretation of spec. 10/12 ML. Viraj and Anish need to close on spec interpretation, then validate the spec with Eileen. Indicate the desired spec here. |  |  | Questionnaire
2017-09-18 |  | Defect - Function | Gil | High | Netwoven | D00006 | Impact All | Dropped code in the Github repository do not reflect either the provided instructions or a working code base. Following is a comparison between what was provided as a reference working example and what was delivered. |  | NCD.1 |  | 2 | 2 | Vendor Bug | ML. Viraj, indicate cause and step(s) taken to address this issue |  |  | Questionnaire Dashboard
2017-09-25 |  | Defect - Function | Gil | High | Netwoven | D00007 |  | Drop #2 NPM Instructions. Documentation does not reflect that the NeuroGraphModule module should be referenced. |  | NCD.1 | Drop 3 | 3 | 2 | Vendor Bug | 9/28 JS - Refer to document in Freedback Defect Tracking file "Gil F_client-side-code-drop-notes-20170927.docx" for details and samples. ML. Viraj, indicate cuase and steps taken to address this issue. |  |  | Graph
2017-09-26 |  | Defect - Function | Gil | High | Netwoven | D00008 | Library Build-Structure | Attempt to install the library per the updated instruction and see that there are a number of peer dependencies that are missing. |  | NCD.1 |  | 2 | 2 | Vendor Bug | 9/28 JS - Refer to document in Freedback Defect Tracking file "Gil F_client-side-code-drop-notes-20170927.docx" for details and samples. ML. Viraj, indicate cause and steps taken to address this issue. |  |  | Demographics Bar
2017-09-26 |  | Defect - Function | Gil | High | Netwoven | D00009 | Library Build-Structure | Attempt to build the imported library into the reference application we provided previously but see a ‘rxjs/subject’ dependency is missing – basically the build fails at this point. |  | NCD.1 |  | 2 | 2 | Vendor Bug | 9/28 JS - Refer to document in Freedback Defect Tracking file "Gil F_client-side-code-drop-notes-20170927.docx" for details and samples. |  |  | Navigation Bar | library
2017-09-26 |  | Defect - Function | Gil | High | Netwoven | D00010 | Library Build-Structure | Attempted to build the library from ‘scratch’ using the code in Github updated 8 hours ago. This process involves a. Git clone repository (https://github.com/SutterRDD/netwoven-ms-graph-component.git) b. Execute a “$ npm install” (to load the library/project’s dependencies) c. Execute a “$ npm run build” and see the same dependency error. |  | NCD.1 |  | 2 | 2 | Vendor Bug | 9/28 JS - Refer to document in Freedback Defect Tracking file "Gil F_client-side-code-drop-notes-20170927.docx" for details and samples. ML. Viraj, indicate cause and steps taken to address this issue. |  |  | Progress Notes
2017-09-29 |  | Defect - Function | Gil | High | Netwoven | D00011 | API | The following API requests do not appear to have been integrated into the component. Documentation - README.md documentation needs to include all component installation instructions Code- Remove all console.log() messaging |  | NCD.1 |  | 2 | 2 | Vendor Bug | ML. Viraj, indicate cause and steps taken to address this issue. |  |  | API
2017-10-03 |  | Defect - Visual | Jackie |  | Jackie | D00012 |  | Missing grey background color | Visio - Default Layers 08132017 MS Share Style Guide 091617 pg. 2 | NCD.1.2 | NCD 3, 10/11/17 | 3 | 3 | Vendor Bug | Refer to "Graph + CDS Cosmetic Issues 10.2.17" document. 10/12 ML. NW fix 10/11,.Jackie to Validate (per next code drop). ML clarify with Viraj . Tanmoy wrote: It was already implemented in local server but at the client side it was not reflected due icon fonts refferals. {ML: meaning this has been resolved on client side?] We are unable to replicate it at our end. |  |  | Library Build-Structure
2017-10-03 |  | Defect - Visual | Jackie | High | Jackie | D00013 | Graph | "Neuro Related" should read "MS Related" | Visio - Default Layers 08132017 | NCD.1.2 | NCD 3, 10/11/17 | 3 | 3 | Vendor Bug | Refer to "Graph + CDS Cosmetic Issues 10.2.17" document 10/12 ML. Netwoven fix 10/11. Jackie to validate at next code drop. |  |  | Impact All
2017-10-03 |  | Defect - Visual | Jackie | High | Jackie | D00014 | Graph | Data element names under MS Related are too smushed together - each group should be evenly spaced apart in relation to the group name (i.e. Treatments, Outcomes, etc.) | Visio - Default Layers 08132017 MS Share Style Guide 091617 pg. 3 | NCD.1.2 | NCD 3, 10/11/17 | 3 | 3 | Vendor Bug | Refer to "Graph + CDS Cosmetic Issues 10.2.17" document 10/12 ML. Netwoven fix 10/11. Jackie to validate at next code drop.
2017-10-03 |  | Defect - Visual | Jackie | High | Jackie | D00015 | Graph | Missing "Add Today" header under "MS Related" above the "+" column | Visio - Default Layers 08132017 | NCD.1.2 | NCD 3, 10/11/17 | 3 | 3 | Vendor Bug | Refer to "Graph + CDS Cosmetic Issues 10.2.17" document 10/12 ML. Netwoven fix 10/11. Jackie to validate next code drop.
2017-10-03 |  | Defect - Visual | Jackie | High | Jackie | D00016 | Graph / EDSS | "i" information button next to "Add Virtual Caseload" should look like the one in the mock-up | Visio - Default Layers 08132017 MS Share Style Guide 091617 pg. 3 | NCD.1.2 | NCD 3, 10/11/17 | 3 | 2 | Vendor Bug | Refer to "Graph + CDS Cosmetic Issues 10.2.17" document 10/12 ML. Netwoven fix 10/11. Jackie to validate next code drop.
2017-10-03 |  | Defect - Visual | Jackie | High | Jackie | D00017 | Graph | Missing horizontal grid lines on graph Vertical grid lines should be solid lines, not dotted lines | Visio - Default Layers 08132017 Graph Specs 082917 pg. 1 | NCD.1.2 | NCD 3, 10/11/17 | 3 | 3 | Vendor Bug | Refer to "Graph + CDS Cosmetic Issues 10.2.17" document 10/12 ML. Netwoven fix 10/11. Anupam says: As per current implementation in case of EDSS we are maintaining the horizontal line. ML: Presume this to mean the horizontal line was there now (and solid vertical 10/12 ML Jackie to validate next code drop.
2017-10-03 |  | Defect - Visual | Jackie | High | Jackie | D00018 | Graph / EDSS | All EDSS values on the graph should be labeled with their value and 1 decimal point, so 2 should be 2.0 | Visio - Default Layers 08132017 | NCD.1.2 | NCD 3, 10/11/17 | 3 | 3 | Vendor Bug | Refer to "Graph + CDS Cosmetic Issues 10.2.17" document 10/12 ML. Netwoven fix 10/11. Jackie to validate next code drop.
2017-10-03 |  | Defect - Function | Jackie | High | Jackie | D00019 | Graph | Missing Push to AVS, Push to Progress Note, and graph Key, Refresh, and Zoom in/out buttons | Visio - Default Layers 08132017 MS Share Style Guide 091617 pg. 4 | NCD.1.2 | NCD 3, 10/11/17 | 3 | 2 | Vendor Bug | Refer to "Graph + CDS Cosmetic Issues 10.2.17" document 10/12 ML. NW fix 10/11,.Jackie to Validate next code drop.
2017-10-03 |  | Defect - Visual | Jackie | High | Jackie | D00020 | CDS | Checkboxes should look like the ones in the mock-up | Visio - Default Layers 08132017 MS Share Style Guide 091617 pg. 3 | NCD.3.1 | NCD 3, 10/11/17 | 3 | 3 | Vendor Bug | Refer to "Graph + CDS Cosmetic Issues 10.2.17" document 10/12 ML. NW fix 10/11,.Jackie to Validate next CD.
2017-10-03 |  | Defect - Visual | Jackie | High | Jackie | D00021 | CDS | Missing "i"information buttons instead of "Submit" next to each CDS activity in the CDS component | Visio - Default Layers 08132017 MS Share Style Guide 091617 pg. 3 | NCD.3.1 | NCD 3, 10/11/17 | 3 | 3 | Vendor Bug | Refer to "Graph + CDS Cosmetic Issues 10.2.17" document 10/12 ML. NW fix 10/11,.Jackie to Validate (per next code drop). ML, clarify with Viraj . Tanmoy wrote: It was already implemented in local server but at the client side it was not reflected due icon fonts refferals. {ML: meaning this has been resolved on client side?] We are unable to replicate it at our end.
2017-10-03 |  | Enhancement | Jackie | High | Jackie | D00022 | Graph | For the graph x-axis scroll bar, bold the years, extend the year tick marks so that they go from the top to the bottom of the bar, and remove the month tick marks from the scroll bar |  | NCD.3.1 | NCD 3, 10/11/17 | 3 | 2 | Missed Specification | Refer to "Graph + CDS Cosmetic Issues 10.2.17" document 10/12 ML. NW fix 10/11,.Jackie to Validate next CD. 10/20 JL: Month tick marks from x-axis were removed as requested, but we wanted to keep the vertical month lines in the graph. Could these be added back in but keep the tick marks off?
2017-10-03 |  | Defect - Function | Jackie | High | Netwoven | D00023 | CDS | "Review relapses" and "Review symptom referrals" CDS activities shouldn't be checked off on the default screen | TECH TEAM 4_MS_MasterSpec_Clinic App_CDS pg 6, 9-10 | NCD.3.1 |  | 1 | 2 | Vendor Bug | 10/12 ML. Viraj, need status update from NW (Sushant). Status was missing.
2017-10-03 |  | Defect - Function | Jackie | High | Netwoven | D00024 | CDS | Missing "x" in the upper right corner of CDS information boxes to close boxes | Visio-CDS Info Panels 081617 | NCD.3.1 |  | 2 | 3 | Vendor Bug | 10/20 JL: Verified "x"s are showing up and functioning correctly
2017-10-03 |  | Defect - Function | Jackie | High | Netwoven | D00025 | CDS | See publication/ Learn more links don't work | Visio-CDS Info Panels 081617 | NCD.3.1 | NCD 3, 10/11/17 | 3 | 2 | Vendor Bug | 10/12 ML: Viraj, will you clarify this status please. NW marked resolved but appears In progress. From 10/11 update sheet ... Sudipto's Comment : Working as expected (redirecting to google.co.in as per API) Swapna's Comment : In lower side checkbox,the CDS information box is not displaying the entire text content . So these links are not visible for some checkboxes.
2017-10-03 |  | Defect - Visual | Jackie | High | Netwoven | D00026 | CDS | Panel is hanging off screen for "Review DMTs" and "Review other symptom meds" CDS information boxes | Visio-CDS Info Panels 081617 | NCD.3.1 |  | 1 | 3 | Vendor Bug | 10/20 JL: Verified panels aren't hanging off screen
2017-10-03 |  | Defect - Visual | Jackie | High | Anish | D00027 | CDS | For the "Review vaccinations" CDS information box, "ageappropriate" should be "age-appropriate", ".,People" should be ". " with "People" starting on a new paragraph | Visio-CDS Info Panels 081617 | NCD.3.1 | NCD 3, 10/11/17 | 3 | 2 | Vendor Bug | 10/12 ML: Anish review this comment from Sudipto noting it's an API fix. Sudipto: Data is coming from API so spelling mistake is in the API mock data. As per the current implementation,the modification of the text present in the CDS information box is not Netwoven Scope. This sholud be taken care by API team. Sudipto: The new paragraph change is done. 10/20 JL: Changed "agerecommended" to "ageappropriate"
2017-10-03 |  | Defect - Visual | Jackie | High | Netwoven | D00028 | CDS | Correct CDS information box typos that were typoed in spec: Review MRI Images: "as well as as a" should be "as well as a" Review MS type/status: Change "Accurate phenotypes MS" to "Accurate MS phenotypes" |  | NCD.3.1 |  | 2 | 2 | Vendor Bug | 10/12 ML: Anish review this comment from Sudipto noting it's an API fix. Sudipto: Data is coming from API so spelling mistake is in the API mock data.
2017-10-04 |  | Defect - Function | Jackie | High | Netwoven | D00029 | Graph / DMTs | Meds aren't displaying by order date from top to bottom, with most recent order first? | TECH TEAM 5_MS_MasterSpec_Clinic APP_Graph EDSS pg. 7 | NCD.1.2 | NCD 4, 10/25/17 | 3 | 2 | Vendor Bug | 10/13 ML: NW to report status on 10/16.
2017-10-04 | 1900-01-04 | Defect - Function | Jackie | High | Netwoven | D00030 | Graph / Other Meds | Meds aren't displaying by order date from top to bottom, with most recent order first? (see MS-SHARE Defect Screenshots slide 2) | TECH TEAM 5_MS_MasterSpec_Clinic APP_Graph Other Meds pg. 8 | NCD.1.2 | NCD 4, 10/25/17 | 3 | 2 | Vendor Bug | 10/13 ML: NW to report status on 10/16.
2017-10-04 |  | Defect - Function | Jackie | High | Netwoven | D00031 | Graph / Vit D | Data level 2 boxes should appear with a hover, and shouldn't require the user to click on it to see the pop-up box | TECH TEAM 5_MS_MasterSpec_Clinic APP_Graph Vitamin D pg. 8 | NCD.1.2 |  | 2 | 2 | Vendor Bug | 10/13 ML: NW to report status on 10/16.
2017-10-04 |  | Defect - Function | Jackie | High | Netwoven | D00032 | Graph / EDSS | Data level 2 boxes should appear with a hover, and shouldn't require the user to click on it to see the pop-up box | TECH TEAM 5_MS_MasterSpec_Clinic App_Graph EDSS pg. 15 | NCD.1.2 |  | 2 | 2 | Vendor Bug | 10/13 ML: NW to report status on 10/16.
2017-10-04 |  | Defect - Function | Jackie | High | Netwoven | D00033 | Graph / EDSS | Information pop-up box should require the user to click on the information button to see the pop-up box - it shouldn't appear just by hovering over the icon | TECH TEAM 5_MS_MasterSpec_Clinic App_Graph EDSS pg. 17 | NCD.1.2 |  | 2 | 3 | Vendor Bug | 10/13 ML: NW to report status on 10/16. 10/20 JL: Verified click instead of hover
2017-10-04 |  | Defect - Visual | Jackie | High | Netwoven | D00034 | Graph / EDSS | Manually added EDSS scores created using the "+" workflow don't save after they're added and the EDSS checkbox is unchecked and then checked again | TECH TEAM 5_MS_MasterSpec_Clinic App_Graph EDSS pg. 15 | NCD.1.2 |  | 2 | 2 | Vendor Bug | 10/13 ML: NW to report status on 10/16.
2017-10-04 |  | Defect - Visual | Jackie | High | Netwoven | D00035 | Graph / EDSS | Should be able to update manually entered EDSS scores | TECH TEAM 5_MS_MasterSpec_Clinic App_Graph EDSS pg. 15 | NCD.1.2 |  | 2 | 3 | Vendor Bug | 10/13 ML: NW to report status on 10/16. 10/20 JL: Verified can update EDSS scores in Chrome,
2017-10-03 |  | Defect - Visual | Jackie | High | Netwoven | D00036 | CDS | Neuro Related Care should read "MS Related Care" | Visio - Default Layers 08132017 | NCD.3.1 |  | 2 | 3 | Vendor Bug | 10/13 ML: NW to report status on 10/16. 10/20 JL: Verified text fix
2017-10-03 |  | Defect - Visual | Jackie | High | Netwoven | D00037 | Graph | Checkboxes should appear as shown in the mock-up with corresponding colors depending on the data element | Visio - Default Layers 08132017 MS Share Style Guide 091617 pg. 3 | NCD.3.1 |  | 2 | 3 | Vendor Bug | 10/13 ML: NW to report status on 10/16. 10/20 JL: Verified checkboxes match mock-ups
2017-10-05 |  | Defect - Function | Jackie | High | Netwoven | D00038 | Graph / Other Meds | Venlafaxine with 2011 end date is displaying on the graph even though the time frame of the graph is 2015-2017 - graph should only show meds within the time frame that is being viewed as shown by the x-axis (see MS-SHARE Defect Screenshots slide 3) |  | NCD.1.2 |  | 2 | 2 | Vendor Bug | 10/13 ML: NW to report status on 10/16.
2017-10-10 |  | Defect - Visual | Jackie | High | Jackie | D00039 | Navigation Bar | Line above the Feedback icon (similar to the one between the Feedback and User's Guide icon) is missing | 1_MS-MasterSpec_Clinic App_Navigation Bar_30Jun17 pg. 3 | ACD.1 | 2017-10-12 | 3 | 3 | Vendor Bug | 10/12 ML. JM reports fix, Jackie to validate next CD.
2017-10-10 |  | Defect - Visual | Jackie | High | Jackie | D00040 | Navigation Bar | Name when hovered over should be "Progress Note" instead of "Progress Notes" and "User's Guide" instead of "Users Guide" | 1_MS-MasterSpec_Clinic App_Navigation Bar_30Jun17 pg. 5 | ACD.1 | 2017-10-12 | 3 | 3 | Vendor Bug | 10/12 ML. JM reports fix, Jackie to validate next CD.
2017-10-10 |  | Defect - Visual | Jackie | High | Jackie | D00041 | Navigation Bar | After clicking on the feedback icon and the dropdown for the screen, the first option should read "MS Care" instead of "MS-Care" | 1_MS-MasterSpec_Clinic App_Navigation Bar_30Jun17 pg. 5 | ACD.1 | 2017-10-12 | 3 | 3 | Vendor Bug | 10/12 ML. JM reports fix, Jackie to validate next CD.
2017-10-10 |  | Defect - Visual | Jackie | High | Jackie | D00042 | Demographics Bar | "neuroSHARE" in the upper left corner should be bolded and SHARE should be in all caps | Visio - Default Layers 08132017 | ACD.1 | 2017-10-12 | 3 | 2 | Vendor Bug | 10/12 ML. JM reports fix, Jackie to validate next CD. 10/20 JL: SHARE should be in all caps too
2017-10-10 |  | Defect - Visual | Jackie | High | Jackie | D00043 | Demographics Bar | Patient Name: patient name should display as patient's [Last Name [Jr/Sr], First name, Middle Initial] instead of [First name Last name] | 1_MS_MasterSpec_Clinic App_Demogrpahics Bar_30Jun17 pg. 4 | ACD.1 | 2017-10-12 | 3 | 3 | Vendor Bug | 10/12 ML. JM reports fix, Jackie can validate test the code drop.
2017-10-10 |  | Defect - Function | Jackie | High | Jackie | D00044 | Demographics Bar | Age of Onset: Shouldn't be able to type in letter "e" "-" "," "+" or "." (e, dash, comma, plus sign, or period) | 1_MS_MasterSpec_Clinic App_Demogrpahics Bar_30Jun17 pg. 4 | ACD.1 | 2017-10-12 | 3 | 2 | Vendor Bug | 10/12 ML. JM reports fix, Jackie can validate test the code drop. 10/19 JL: Unable to type in any numeric values - if possible, prefer to keep the ability to type only numeric values OR use the arrows to change the age?
2017-10-10 |  | Enhancement | Jackie | High | Jackie | D00045 | Demographics Bar | Age of Onset: Should be a character field limit - currently doesn't seem to be a limit? |  | ACD.1 | 2017-10-12 | 3 | 3 | Missed Specification | 10/12 ML. JM reports fix, Jackie can validate test the code drop.
2017-10-10 |  | Defect - Function | Jackie | High | Jackie | D00046 | Demographics Bar | Age of Onset: Should be able to hover over a completed age of onset field and see the date of completion | 1_MS_MasterSpec_Clinic App_Demogrpahics Bar_30Jun17 pg. 5 | ACD.1 | 2017-10-12 | 3 | 2 | Vendor Bug | 10/12 JM. API not supporting this field. API updates and UI as well. 10/12 ML. Anish, please review re API. 10/12 ML. JM reports fix, Jackie to validate next CD. 10/19 JL: Change hover text format to “Entered on [MM/DD/YY]”
2017-10-10 |  | Defect - Visual | Jackie | High | Jackie | D00047 | Demographics Bar | MS Type: MS types in dropdown should display as the full names. Truncated/abbreviated names show once the selection has been made and display in the field | 1_MS_MasterSpec_Clinic App_Demogrpahics Bar_30Jun17 pg. 5 | ACD.1 | 2017-10-12 | 3 | 2 | Vendor Bug | 10/12 JM. API not returning full disease name. API updated. UI fixed as well. 10/12 ML. Anish, please review re API. 10/12 ML. JM reports fix, Jackie to validate next CD. 10/20 JL: Add hyphen between "Relapsing-Remitting" and "Progressive-Relapsing"
2017-10-10 |  | Defect - Function | Jackie | High | Jackie | D00048 | Demographics Bar | MS Type: Should be able to hover over a completed MS type field and see the full name and date of completion | 1_MS_MasterSpec_Clinic App_Demogrpahics Bar_30Jun17 pg. 5 | ACD.1 | 2017-10-12 | 3 | 2 | Vendor Bug | 10/12 JM. API not supporting this field. API updates and UI as well. 10/12 ML. Anish, please review re API. 10/12 ML. JM reports fix, Jackie to validate next CD. 10/19 JL: Change hover text format to “Entered on [MM/DD/YY]”
2017-10-16 |  | Defect - Function | Jackie |  | Jackie | D00049 | Demographics Bar | MS Status: Should be able to hover over a completed MS status field and see the date of completion |  | ACD.1 |  |  | 3 | Vendor Bug | 10/19 JL: Change hover text format to “Entered on [MM/DD/YY]”
2017-10-16 |  | Defect - Function | Jackie |  | Jackie | D00050 | Graph / Relapses | If you click too fast to display relapses on the graph and then uncheck the checkbox, the relapses will still load and display on the graph but the checkbox remains unchecked - the checkbox status should match whether or not the data elements are displayed on the graph | TECH TEAM 5_MS_MasterSpec_Clinic App_Graph Relapses pg. 7 | NCD.2.1 |  | 1 | 1 | Vendor Bug
2017-10-16 |  | Spec Mismatch | Jackie |  | Jackie | D00051 | Graph / Relapses | Month dropdown should default to "Month" and Year dropdown should default to "Year", not "January" and "2017" as it currently does | TECH TEAM 5_MS_MasterSpec_Clinic App_Graph Relapses pg. 8 | NCD.2.1 |  | 2 | 1 | Vendor Bug
2017-10-16 |  | Defect - Function | Jackie |  | Jackie | D00052 | Graph / Relapses | Manually added relapses aren't showing up at the month and year that was entered and when the symbol is clicked on, the month dropdown says "monthSel" - manually added relapses should appear with a symbol on the respective month and year and the month dropdown should show the selected month | TECH TEAM 5_MS_MasterSpec_Clinic App_Graph Relapses pg. 9-10 | NCD.2.1 |  | 2 | 1 | Vendor Bug
2017-10-16 |  | Defect - Visual | Jackie |  | Jackie | D00053 | Graph / Labs | Some lab symbols are floating to the left of the graph in the MS Related panel in Internet Explorer only - should only see symbols for data elements in the graph (see MS-SHARE Defect Screenshots slide 4) |  | NCD.1.3 | NCD 4, 10/25/17 | 3 | 1 | Vendor Bug
2017-10-17 |  | Defect - Function | Jackie |  | Jackie | D00054 | Graph / Imaging | IE only: Report doesn't open when icon is clicked - should open |  | NCD.2.2 | NCD 4, 10/25/17 | 3 | 1 | Vendor Bug
2017-10-17 |  | Defect - Visual | Jackie |  | Jackie | D00055 | Graph / Imaging | ON HOLD: Jackie needs to revise issue text. Imaging symbols on the graph should be half filled if not all of the images for that date have been resulted - the imaging symbols currently only show 1 study with resulted items and 1 study without any resulted, but the symbols are filled. They should be half filled according to this logic. | TECH TEAM 5_MS_MasterSpec_Clinic App_Graph Imaging pg. 10 | NCD.2.2 |  |  | 1 | Vendor Bug | 10/20 JL: Original documented defect is incorrect - Jackie to revise issue text with potential enhancement instead
2017-10-17 |  | Spec Mismatch | Jackie |  | Jackie | D00056 | Patient Concerns | Free text in comment boxes should be specific to that patient concern and that action - currently, free text typed into a comment box and saved will carry over to other actions under that patient concern |  | ACD.1 |  |  | 1 | Vendor Bug
2017-10-17 |  | Defect - Function | Jackie |  | Jackie | D00057 | Patient Concerns | Free text comment box should not appear for "Disability forms completed" option under New work-related needs | TECH TEAM 5_MS_MasterSpec_Clinic App_Pt Concerns_09-06-17 pg. 8 | ACD.1 |  |  | 2 | Vendor Bug | 10/20 JL: Verified free text box doesn't auto appear, but the expand/collapse button still appears - expand/collapse button shouldn't appear for options with free text box
2017-10-17 |  | Defect - Function | Jackie |  | Jackie | D00058 | Patient Concerns | Free text boxes should only appear for actions that have a free text option in the spec "Other"x4, "Discussed side effects management", "Discussed symptom management medications", "Advised to ***", and "Addressed") - currently, all actions have a free text box when the component is expanded | TECH TEAM 5_MS_MasterSpec_Clinic App_Pt Concerns_09-06-17 pg. 8 | ACD.1 |  |  | 1 | Vendor Bug
2017-10-17 |  | Spec Mismatch | Jackie |  | Jackie | D00059 | Patient Concerns | Expand/collapse icon should only appear/be active when an action with a free text option has been selected | TECH TEAM 5_MS_MasterSpec_Clinic App_Pt Concerns_09-06-17 pg. 4 | ACD.1 |  |  | 2 | Vendor Bug | 10/20 JL: Expand/collapse icon still appears fro "disability forms completed"
2017-10-20 |  | Spec Mismatch | Jackie |  |  | D00060 | Patient Concerns | "Advised to ***" should be changed to "Advised to…" | TECH TEAM 5_MS_MasterSpec_Clinic App_Pt Concerns_09-06-17 pg. 5 | ACD.1
2017-10-20 |  | Spec Mismatch | Jackie |  |  | D00061 | Patient Concerns | The "other" patient concern should show all of the time by default, regardless of the expanded or collapsed status of the component - currently, the text description (not the provider free texted action) that the patient typed for the "other" patient concern is only showing when the "adressed" action is selected or when the component is expanded |  | ACD.1
2017-10-20 |  | Defect - Function | Jackie |  |  | D00062 | Demographics Bar | IE only: Should be able to edit the Age of Onset field by manually entering in numeric values or using the arrows - currently can't edit |  | ACD.1
2017-10-20 |  | Enhancement | Jackie |  |  | D00063 | Demographics Bar | Spec error - MS Type: Change "Progressiving-Relapsing" to "Progressive-Relapsing" |  | ACD.1
2017-10-20 |  | Defect - Visual | Jackie |  |  | D00064 | Demographics Bar | MS Status: Change "Non Active" to "Not Active" | 1_MS_MasterSpec_Clinic App_Demographics Bar_30Jun17 pg. 6 | ACD.1
2017-10-20 |  | Defect - Visual | Jackie |  |  | D00065 | Demographics Bar | MS Status: Change "Non Progressing" to "Not Progressing" | 1_MS_MasterSpec_Clinic App_Demographics Bar_30Jun17 pg. 6 | ACD.1
2017-10-20 |  | Defect - Function | Jackie |  |  | D00066 | Demographics Bar | Last Visit with Me: Should be a read only field - currently, can hover over field and mouse changes as if it's a clickable field | 1_MS_MasterSpec_Clinic App_Demographics Bar_30Jun17 pg. 7 | ACD.1
2017-10-20 |  | Spec Mismatch | Jackie |  |  | D00067 | Demographics Bar | Information button: Information pop-up box should behave like the MS Related Care pop-up boxes |  | ACD.1
2017-10-20 |  | Enhancement | Jackie |  |  | D00068 | Demographics Bar | Information button: Change "Progressing Relapsing" to "Progressive-Relapsing" and add hyphen to "Relapsing-Remitting" |  | ACD.1
D00069
D00070
D00071
D00072
D00073
D00074
D00075
D00076
D00077
D00078
D00079
D00080
D00081
D00082
D00083
D00084
D00085
D00086
D00087
D00088
D00089
D00090
D00091
D00092
D00093
D00094
D00095
D00096
D00097
D00098
D00099
D00100
D00101
D00102
D00103
D00104
D00105
D00106
D00107
D00108
D00109
D00110
D00111
D00112
D00113
D00114
D00115
D00116
D00117
D00118
D00119
D00120
D00121
D00122
D00123
D00124
D00125
20
Note on C8: Mike 11/11 added "Spec Mismatch" to defect type (column C), added "Develop 'Fix Release, Date' (column L).
Note on K8: Release: Find Release in 'Code Drop and Test Schedule.xlsx' … in Freedcamp Project Mgt folder
Note on M20: see comments

## list
Pass | GET, PUT, | Response | Errors | APIs Utilized | Basic Purpose for Integration | Mock / Live | Notes
| POST | (ms) |  |  |  | Data
| POST |  |  | ms/cds | Create a new CDS record |  | No POST issued on click
| PUT |  |  | ms/cds | Update an existing CDS record |  | No PUT on click
| GET |  |  | ms/ms-population-data | Retrieves EDSS scores from UCSF |  | Does not appear to be integrated